## Index
Sheet | Slide | Chart | Categories | Series
S05_Commercial | S05 | S05_Commercial | 2 | 3
S05_FTRI | S05 | S05_FTRI | 2 | 1
S05_NearMisses | S05 | S05_NearMisses | 1 | 1
S05_Inductions | S05 | S05_Inductions | 1 | 1
S05_OpenNCR | S05 | S05_OpenNCR | 1 | 1
S06_DD | S06 | S06_DD | 1 | 1
S06_GFC | S06 | S06_GFC | 1 | 1
S08_BIM | S08 | S08_BIM | 6 | 4
S09_Trend | S09 | S09_Trend | 3 | 1
S09_Hotspots | S09 | S09_Hotspots | 6 | 1
S12_4H | S12 | S12_4H | 1 | 1
S12_3H | S12 | S12_3H | 1 | 1
S12_Convention | S12 | S12_Convention | 1 | 1
S13_Manpower | S13 | S13_Manpower | 2 | 1
S17_ValueMix | S17 | S17_ValueMix | 3 | 1
S20_EHS | S20 | S20_EHS | 4 | 2
S27_Leading | S27 | S27_Leading | 5 | 1
S27_Lagging | S27 | S27_Lagging | 6 | 1
S27_FTRI | S27 | S27_FTRI | 2 | 1
S28_Observations | S28 | S28_Observations | 2 | 1
S28_NCR | S28 | S28_NCR | 2 | 1

## S05_Commercial
| Actual | Revamp Plan | Baseline
FTM | 15.5 | 15.56 | 8.94
CUM | 37.8 | 16.2 | 60

## S05_FTRI
FTRI Score
Achieved | 0.88
Gap | 0.12

## S05_NearMisses
Near Misses
Near Misses | 4

## S05_Inductions
Inductions
Inductions | 1691

## S05_OpenNCR
Open NCR
Open NCR | 1

## S06_DD
DD Approved
DD Approved | 1014

## S06_GFC
GFC Approved
GFC Approved | 178

## S08_BIM
| Architecture | Structure | MEPF | BOH
Substructure | 84 | 80 | 82 | 85
3H Hotel | 83 | 82 | 86 | 89
4H Hotel | 82 | 81 | 84 | 87
Retail 1 | 86 | 75 | 83
Retail 2 | 86 | 83 | 86
Convention | 83 | 85 | 86 | 76

## S09_Trend
Total Clashes
17 Aug | 15297
24 Aug | 34845
27 Aug | 17400

## S09_Hotspots
Count
MEPF vs AR | 5131
LA vs MEPF | 2233
MEPF vs ST | 1957
AR vs ST | 1576
LA vs ST | 1339
LA vs LA | 1073

## S12_4H
4-H Hotel
4-H Hotel | 39

## S12_3H
3-H Hotel
3-H Hotel | 15

## S12_Convention
Convention Centre
Convention Centre | 8

## S13_Manpower
Workmen
Available | 1032
Sept Plan | 1205

## S17_ValueMix
₹ Cr
Supply | 24
Service | 12.5
Design | 1

## S20_EHS
| FTM | ITD
Inductions | 585 | 1691
Safety Observations | 122 | 781
Tool Box Talks | 265 | 615
Training Sessions | 35 | 109

## S27_Leading
Count
Training Imparted | 74
Good/Best Practices | 16
Material Approvals | 12
Management Walkdown | 9
Mockups | 5

## S27_Lagging
Count
Obs. External | 32
Obs. Internal | 15
Rejection | 1
Repetitive Dev. | 0
Snag Issued | 0
Stop Work | 0

## S27_FTRI
FTRI Score
Achieved | 0.88
Gap | 0.12

## S28_Observations
Observations
Closed | 24
Open | 8

## S28_NCR
NCR
Closed | 103
Open | 20

## RAG_Rules
Indicator | Basis | Green | Amber | Red | Value | Status
Contract value | commercial fact | issued / complete | scheduled / in progress | overdue / not started | ₹1,725 Cr | G
Contract duration | commercial fact | issued / complete | scheduled / in progress | overdue / not started | 39 months | G
Completion date | schedule exposure from commercial slippage | issued / complete | scheduled / in progress | overdue / not started | 15 May 2029 | A
Project health | composite of commercial, design and construction | issued / complete | scheduled / in progress | overdue / not started | Watchlist | A
Commercial FTM vs baseline | variance | >= -5% | -5 to -20% | < -20% | -61% | R
Commercial CUM vs baseline | variance | >= -5% | -5 to -20% | < -20% | -67% | R
Gap to close | ₹76.2 Cr over 33 months | issued / complete | scheduled / in progress | overdue / not started | ₹76.2 Cr | R
First Time Right index | quality_ftri | >= 95% | 85 - 94.9% | < 85% | 88% | A
Safe man-hours ITD | 3,44,498 with zero LTI | issued / complete | scheduled / in progress | overdue / not started | 3,44,498 | G
Lost time injuries | zero_harm | 0 | 1 - 4 | >= 5 | 0 | G
Near misses / HPI | zero_harm | 0 | 1 - 4 | >= 5 | 4 | A
Safety inductions vs plan | progress | >= 90% | 70 - 89.9% | < 70% | 1,691 of 2,400 | A
Open NCR | backlog | <= 50 | 51 - 200 | > 200 | 1 | G
DD approval rate | approval | >= 90% | 75 - 89.9% | < 75% | 1,014 of 1,220 · 83% | A
GFC approval rate | approval | >= 90% | 75 - 89.9% | < 75% | 178 of 247 · 72% | R
Design approval backlog | backlog | <= 50 | 51 - 200 | > 200 | 239 drawings | R
Façade package | design cannot start until commercials close | issued / complete | scheduled / in progress | overdue / not started | Critical | R
DD approved · Architectural | progress | >= 90% | 70 - 89.9% | < 70% | 372 of 372 | G
DD approved · Structural | progress | >= 90% | 70 - 89.9% | < 70% | 182 of 182 | G
DD approved · MEP | progress | >= 90% | 70 - 89.9% | < 70% | 371 of 791 | R
DD approved · Façade | progress | >= 90% | 70 - 89.9% | < 70% | 0 of 235 | R
DD approved · Landscape | progress | >= 90% | 70 - 89.9% | < 70% | 48 of 103 | R
DD approved · BOH (Kitchen) | progress | >= 90% | 70 - 89.9% | < 70% | 0 of 128 | R
DD approved · VT | progress | >= 90% | 70 - 89.9% | < 70% | 41 of 41 | G
DD approved · IT-ICT & Security | progress | >= 90% | 70 - 89.9% | < 70% | 0 of 208 | R
DD approved · Interior & FOH/BOH | progress | >= 90% | 70 - 89.9% | < 70% | 0 of 1012 | R
DD approved · Total | progress | >= 90% | 70 - 89.9% | < 70% | 1014 of 3313 | R
Foundation GFC | R0 issued, optimised revision released | issued / complete | scheduled / in progress | overdue / not started | Issued | G
Structural GFC released | progress | >= 90% | 70 - 89.9% | < 70% | 3 of 5 | R
Architectural GFC | scheduled 22 - 29 Sep, not yet issued | issued / complete | scheduled / in progress | overdue / not started | Scheduled | A
MEPF GFC | scheduled 22 Sep - 14 Oct, not yet issued | issued / complete | scheduled / in progress | overdue / not started | Scheduled | A
BIM overall model maturity | progress | >= 90% | 70 - 89.9% | < 70% | 83.4% | A
BIM highest block · 3H BOH | progress | >= 90% | 70 - 89.9% | < 70% | 89% | A
BIM lowest block · Retail 1 Structure | progress | >= 90% | 70 - 89.9% | < 70% | 75% | A
Blocks under model control | 6 blocks × 4 disciplines | issued / complete | scheduled / in progress | overdue / not started | 6 | G
Clash inventory 17 Aug | clash | <= 5,000 | 5,001 - 20,000 | > 20,000 | 15,297 | A
Clash inventory 24 Aug | clash | <= 5,000 | 5,001 - 20,000 | > 20,000 | 34,845 | R
Clash inventory 27 Aug | clash | <= 5,000 | 5,001 - 20,000 | > 20,000 | 17,400 | A
Clash reduction peak to date | 17,445 clashes closed in three days | issued / complete | scheduled / in progress | overdue / not started | -50% | G
Clash hotspot · MEPF vs AR | hotspot | < 2,000 | 2,000 - 5,000 | > 5,000 | 5,131 | R
Clash hotspot · LA vs MEPF | hotspot | < 2,000 | 2,000 - 5,000 | > 5,000 | 2,233 | A
Clash hotspot · MEPF vs ST | hotspot | < 2,000 | 2,000 - 5,000 | > 5,000 | 1,957 | G
Clash hotspot · AR vs ST | hotspot | < 2,000 | 2,000 - 5,000 | > 5,000 | 1,576 | G
Clash hotspot · LA vs ST | hotspot | < 2,000 | 2,000 - 5,000 | > 5,000 | 1,339 | G
Clash hotspot · LA vs LA | hotspot | < 2,000 | 2,000 - 5,000 | > 5,000 | 1,073 | G
NSC packages released | progress | >= 90% | 70 - 89.9% | < 70% | 6 of 17 | R
Initial submissions complete | 6 packages submitted | issued / complete | scheduled / in progress | overdue / not started | 6 | G
Packages due by 15 Sep | immediate action window | issued / complete | scheduled / in progress | overdue / not started | 5 | A
Forward pipeline | planned 20 Sep - 20 Oct | issued / complete | scheduled / in progress | overdue / not started | 6 | A
Civil package | rebar vendor award by 15 Sep | issued / complete | scheduled / in progress | overdue / not started | On track | G
MEP package | LPS onboarded, NSC vendors open | issued / complete | scheduled / in progress | overdue / not started | Watchlist | A
Façade and ID packages | ID not issued, façade tender pending | issued / complete | scheduled / in progress | overdue / not started | Critical | R
Formwork delivered to site | progress | >= 90% | 70 - 89.9% | < 70% | 1,500 of 7,700 m² | R
Slab formwork · Received | at site | issued / complete | scheduled / in progress | overdue / not started | 1,500 m² | G
Slab formwork · Committed | by 20 Sep | issued / complete | scheduled / in progress | overdue / not started | 1,700 m² | A
Slab formwork · Pipeline | order by 11 Sep | issued / complete | scheduled / in progress | overdue / not started | 10,000 m² | R
Monthly concrete vs plan | progress | >= 90% | 70 - 89.9% | < 70% | 3,025 of 5,584 m³ | R
Workmen vs plan | progress | >= 90% | 70 - 89.9% | < 70% | 1,032 of 1,000 | G
Staff deployed | 142 against requirement | issued / complete | scheduled / in progress | overdue / not started | 142 | G
Foundations complete | progress | >= 90% | 70 - 89.9% | < 70% | 62 of 147 | R
Foundations · 4-H Hotel | progress | >= 90% | 70 - 89.9% | < 70% | 39 of 46 | A
Foundations · 3-H Hotel | progress | >= 90% | 70 - 89.9% | < 70% | 15 of 51 | R
Foundations · Convention Centre | progress | >= 90% | 70 - 89.9% | < 70% | 8 of 50 | R
September manpower plan | +173 net augmentation required | issued / complete | scheduled / in progress | overdue / not started | 1,205 | A
Workmen available vs plan | progress | >= 90% | 70 - 89.9% | < 70% | 1,032 of 1,000 | G
Tower cranes installed | progress | >= 90% | 70 - 89.9% | < 70% | 3 of 5 | R
Workmen sheds erected | progress | >= 90% | 70 - 89.9% | < 70% | 1 of 5 occupied | R
September planned value | forward plan, not yet earned | issued / complete | scheduled / in progress | overdue / not started | ₹37.5 Cr | A
September supply plan | forward plan | issued / complete | scheduled / in progress | overdue / not started | ₹24.0 Cr | A
September service plan | forward plan | issued / complete | scheduled / in progress | overdue / not started | ₹12.5 Cr | A
September design plan | forward plan, low exposure | issued / complete | scheduled / in progress | overdue / not started | ₹1.0 Cr | G
September W1 M40 pour | vs 3,025 m³ achieved in August | issued / complete | scheduled / in progress | overdue / not started | 1,943 m³ | A
September W2 M40 pour | vs 3,025 m³ achieved in August | issued / complete | scheduled / in progress | overdue / not started | 2,553 m³ | A
September W3 M40 pour | vs 3,025 m³ achieved in August | issued / complete | scheduled / in progress | overdue / not started | 1,946 m³ | A
September W4 M40 pour | vs 3,025 m³ achieved in August | issued / complete | scheduled / in progress | overdue / not started | 3,584 m³ | R
September quantity · M40 Supply | against 3,025 m³ August run-rate | issued / complete | scheduled / in progress | overdue / not started | 10,344 m³ | R
September quantity · M40 Service | against 3,025 m³ August run-rate | issued / complete | scheduled / in progress | overdue / not started | 10,344 m³ | R
September quantity · Reinforcement | against 3,025 m³ August run-rate | issued / complete | scheduled / in progress | overdue / not started | 3,000 MT | R
September quantity · M10 Supply + Service | against 3,025 m³ August run-rate | issued / complete | scheduled / in progress | overdue / not started | 405 m³ | A
Statutory items closed | progress | >= 90% | 70 - 89.9% | < 70% | 1 of 4 | R
Statutory · BG Amendment | ALACL input pending | issued / complete | scheduled / in progress | overdue / not started | ALACL input pending | R
Statutory · Policy Amendment | Updated | issued / complete | scheduled / in progress | overdue / not started | Updated | G
Statutory · Labour Licence | Closure required | issued / complete | scheduled / in progress | overdue / not started | Closure required | A
Statutory · BOCW | Expected 05 Sep | issued / complete | scheduled / in progress | overdue / not started | Expected 05 Sep | A
Safe man-hours FTM | zero lagging incidents in the month | issued / complete | scheduled / in progress | overdue / not started | 1,27,954 | G
Safe man-hours ITD | zero lagging incidents to date | issued / complete | scheduled / in progress | overdue / not started | 3,44,498 | G
Fatalities and lost time injuries | zero_harm | 0 | 1 - 4 | >= 5 | 0 | G
High-potential incidents and near misses | zero_harm | 0 | 1 - 4 | >= 5 | 4 | A
First Time Right index | quality_ftri | >= 95% | 85 - 94.9% | < 85% | 88% | A
Training effort imparted | 74 hours delivered | issued / complete | scheduled / in progress | overdue / not started | 74 | G
Good and best practices | 16 recorded in the month | issued / complete | scheduled / in progress | overdue / not started | 16 | G
Deviation closure turnaround | tat_days | <= 14 d | 14 - 21 d | > 21 d | 19.9 days | A
Quality lagging · Obs. External | open defect count | issued / complete | scheduled / in progress | overdue / not started | 32 | R
Quality lagging · Obs. Internal | open defect count | issued / complete | scheduled / in progress | overdue / not started | 15 | A
Quality lagging · Rejection | open defect count | issued / complete | scheduled / in progress | overdue / not started | 1 | A
Quality lagging · Repetitive Dev. | open defect count | issued / complete | scheduled / in progress | overdue / not started | 0 | G
Quality lagging · Snag Issued | open defect count | issued / complete | scheduled / in progress | overdue / not started | 0 | G
Quality lagging · Stop Work | open defect count | issued / complete | scheduled / in progress | overdue / not started | 0 | G
Quality · Skill Ratio | monthly outcome | issued / complete | scheduled / in progress | overdue / not started | 0.60 | A
Quality · Flash Report | monthly outcome | issued / complete | scheduled / in progress | overdue / not started | 0 | G
Quality · Deviation Closure in TAT | monthly outcome | issued / complete | scheduled / in progress | overdue / not started | 19.9 days | A
MOM p1 action 1 · Design Coordination — | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p1 action 2 · Vendor & Consultant | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | WIP | A
MOM p1 action 3 · Workshop Planning & | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p1 action 4 · BIM versus 2D | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p2 action 1 · Detailed Design | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | WIP | A
MOM p2 action 2 · B3 Ceiling Layout | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p2 action 3 · Design Input Tracker | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p2 action 4 · VE Façade Intent | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p2 action 5 · Meeting Agenda | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | WIP | A
MOM p2 action 6 · Landscape & External | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | WIP | A
MOM p2 action 7 · Utility Rooms | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p2 action 8 · Leak-Proof Cut-Out | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 1 · Vendor List Submission | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 2 · Tendering & Technical | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 3 · Package Strategy | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 4 · RFP Finalisation | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 5 · NSC Vendor Onboarding | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 6 · Physical & Financial | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | Closed | G
MOM p3 action 7 · Resource & Quantity | action status from the TPL update | issued / complete | scheduled / in progress | overdue / not started | WIP | A
Observation closure rate | approval | >= 90% | 75 - 89.9% | < 75% | 24 of 32 · 75% | A
Open observations | backlog | <= 50 | 51 - 200 | > 200 | 8 open | G
NCR closure rate | approval | >= 90% | 75 - 89.9% | < 75% | 103 of 123 · 84% | A
Trainings delivered | 44 sessions, 450 man-hours | issued / complete | scheduled / in progress | overdue / not started | 44 | G